## Procurement Datasheet Annex 1
Annexure-1 : Only SPIU details to be filled in this file
State Procurement Activities Data Sheet under STRIVE
Table 1: Contracts awarded under the Program component :
(Enter dates for EOI issuance and Contract Effectiveness. This will help to identify any delays in the procurement cycle and address the challenges.)
S.No. | Name of Procuring Entity | Results Area of Program | Description of Contract | Method of Procurement/Selection | Date of EOI/IFB Issuance | Date of Contract Signature | Date of Contract Effectiveness | Value of Contract [INR]
1 | UT PIU | 2 | Capacity Building | Direct | 2021-11-16 | 2021-11-16 | 2021-11-16 | 7.2
2 | UT PIU | 2 | Capacity Building | Direct | 2021-11-23 | 2021-11-23 | 2021-11-23 | 14.72
3
4
Table 2: Status of items presently under procurement for the Program component (If any)
(Enter all dates that are applicable)
S.No. | Name of Procuring Entity | Results Area of Program | Description of Procurement | Method of Procurement/Selection | Estimated Cost [INR] | Date of EOI/IFB Issuance | Date of RFP issuance | Date of technical proposal opening | Date of financial proposal opening | Date of contract award decision | Duration of Contract [Months]
1 | UT PIU | 2 | Capacity Building | Direct | 2500000 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 | 2022-05-01 | one month
2 | UT PIU | 2 | IT labs | Online | 10000000 | NIL | 2022-02-17 | 2022-02-26 | 2022-05-28 | 2022-05-01 | 90 days
3 | UT PIU | 2 | Consultancy service | Online | 2400000 | 2022-04-07 | 2022-04-25 | 2022-05-05 | 4 Months | 2022-09-01
4 | UT PIU | 2 | Tracer Study | Online | 1800000 | 2022-04-07 | 2022-04-25 | 2022-05-05 | 4 Months | 2022-09-01
5 | UT PIU | 2 | Placement | Online | 2000000 | 2022-04-07 | 2022-04-25 | 2022-05-05 | 4 Months | 2022-09-01
Table 3: Implementing agency (IA) wise status update regarding publishing of procurement plans (PP) along with URL of the web page where it is published.
S.No. | Name of Procuring Entity | Results Area of Program | PP published? (Yes/ No) | URL of published PP | CAN Published [Yes/No] | URL of published CAN
1 | UT PIU | 2 | Yes |  | YES | http://jkdsd.in/strive/220318-Contract-Award-Notice.pdf
https://jkdsd.in/strive/ra-2-action-plan.pdf
https://jkdsd.in/strive/ra-2-bidding-a.pdf
https://jkdsd.in/strive/ra-2-bidding.pdf
https://jkdsd.in/strive/ra-2-furniture.xlsx
https://jkdsd.in/strive/ra-2-impa-invoice.pdf
https://jkdsd.in/strive/ra-2-ut-sc.pdf
http://jkdsd.in/strive/220103-pap-formats.pdf
http://jkdsd.in/strive/
http://jkdsd.in/strive/220318-Desktop-Bid.pdf
http://jkdsd.in/strive/220318-Furniture-Bid.pdf
NOTE 1 : | Firms on Bank's list of Ineligible Firms and Individuals are not eligible for award of Contract under STRIVE
NOTE 2: | The program excludes procurement activities above a certain threshold specified in Para 4.2.1 on Page 104 of the Operations Manual

## Sheet1 (hidden)
Results Area of Program
RA 1
RA 2
RA 4
Yes
No