## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : ut Jammu and Kashmir
Annual Procurement Plan for Financial Year : |  |  |  |  | 2022-23
Date of Approval of Annual Procurement Plan :
Approved By/Name of Approving Authority :
S. No. | Procurement Category | Full Name of Procuring Entity (SPIU/ ITI/ SAMC/ IC) | NCVT MIS code in case of ITI (10 characters) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date | Remarks
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19] | [20]
1 | Capacity Building of Principals/Superintendents/Directorate officers | UT PIU | NIL | Capacity Building of Principals/Superintendents/Directorate officers | 25 | 2 | off line | GRF 17 | No | No | Manually | National | 2021-12-13 | 2021-11-16 | 2022-01-15 | 2021-11-16 | 2 | 2022-01-15 | Tarining In process
2 | Short term refreshers course of One/Two weeks duration for Supervisors/Group Instructors | UT PIU | NIL | Short term refreshers course of One/Two weeks duration for Supervisors/Group Instructors | 15 | 2 | off line | GRF 17 | No | No | Manually | National | 2021-12-13 | 2021-11-16 | 2022-01-15 | 2021-11-16 | 2 | 2022-01-15 | Tarining In process
3 | Short term refreshers course ofOne/Two weeks duration for Ministerial Staff | UT PIU | NIL | Short term refreshers course ofOne/Two weeks duration for Ministerial Staff | 15 | 2 | off line | GRF 17 | No | No | Manually | National | 2021-12-13 | 2021-11-16 | 2022-01-15 | 2021-11-16 | 2 | 2022-01-15 | Tarining In process
4 | Setting up of IT Labs for ITIs not funded under any Scheme | UT PIU | NIL | Setting up of IT Labs for ITIs not funded under any Scheme | 100 | 2 | online | GRF 17 | Yes | Yes | GEM | National | 2021-10-02 | 2021-09-25 | 2021-10-18 | 2021-10-18 | 16 days | 2021-10-18 | Re-tendering
5 | Conducting of Awareness Camps/Seminars/Workshops/Placement Drivers/RozgarMelas/Publicity through Print/Electronic Media etc. for encouraging women folk and persons belongs from disadvanagoues groups | UT PIU | NIL | Conducting of Awareness Camps/Seminars/Workshops/Placement Drivers/RozgarMelas/Publicity through Print/Electronic Media etc. for encouraging women folk and persons belongs from disadvanagoues groups | 14 | 2 | off line | GRF 17 | No | No | Manually | National | Under Process | Under Process | Under Process | Under Process | Under Process | Under Process
6 | Funds Utilization at Directorate Level for defined component@600000 during Winter/Summer Darbar Move at Jammu/Srinagar | UT PIU | NIL | Funds Utilization at Directorate Level for defined component@600000 during Winter/Summer Darbar Move at Jammu/Srinagar | 12 | 2 | off line | GRF 17 | No | No | Manually | National | Under Process | Under Process | Under Process | Under Process | Under Process | Under Process
7 | Hiring of Consultants | UT PIU | NIL | Hiring of Consultants | 48 | 2 | online | GRF 17 | Yes | Yes | GEM | National | Under Process | Under Process | Under Process | Under Process | Under Process | Under Process
8 | Conduct Tracer Study | UT PIU | NIL | Conduct Tracer Study | 6 | 2 | online | GRF 17 | Yes | Yes | GEM | National | Under Process With SLPC
8 | Strengthening of Placements cell at Joint Directorate Level. Outsourcing of placement activities through relevant outsourcing agencies for 2 years | UT PIU | NIL | Strengthening of Placements cell at Joint Directorate Level. Outsourcing of placement activities through relevant outsourcing agencies for 2 years | 20 | 2 | online | GRF 17 | Yes | Yes | GEM | National | Under Process With SLPC
10 | NIL | Anantnag | GR01000003 | NIL
11 | Nil | Baramulla | GR01000004 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
12 | Goods | Ganderbal | GR01000040 | 3180 | RA 1 | Online | GFR-2017 | Yes | No | Online | National | 06.08.2022 |  | 18.08.2022 |  | 15 Days | 2022-08-31
13 | Goods | Ganderbal | GR01000040 | 2, 91, 880 | RA 1 | Online | GFR-2017 | Yes | No | Online | National | 04.08.2022 |  | 18.08.2022 |  | 15 Days | 2022-08-31
14 | Equipment , furniture& other goods | Samba | GR01000035 | Equipment , furniture& other goods purchase for copa,Electrician,Sewing Technology,Lib/./Office/GYM | 5025000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
15 | Traininf of teaching & management staff | Samba | GR01000035 | Training to be arranged in jk UT /outside the UT | 500000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
16 | Purchase of books & other learning materials | Samba | GR01000035 | Funds to be utilized for different trades | 900000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30days | 2022-09-01
17 | Facilites of trainees | Samba | GR01000035 | OJT/other facilites to be provided to the trainees of different trades | 300000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
18 | Miscellaneous | Samba | GR01000035 | Misc exp. (Raw material etc) | 500000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
19 |  | Samba | GR01000035 | Training to be arranged in jk UT /outside the UT | 500000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
20 |  | Samba | GR01000035 | Funds to be utilized for different trades | 900000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30days | 2022-09-01
21 |  | Samba | GR01000035 | OJT/other facilites to be provided to the trainees of different trades | 300000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
22 |  | Samba | GR01000035 | Misc exp. (Raw material etc) | 500000 | RA1 | Online | GFR-2017 & JKUT Financial Norms | YES | YES | GEM | National | 2022-07-01 |  | 2022-09-01 |  | 30 days | 2022-09-01
23 | Goods | Udhampur | GU01000011 | Equipment,Furniture etc | 4601000 | RA 1 | Offline/Online | GFR 2017 and JKUT Financial rules | Yes | Yes | Direct/Bidding | National | 44851 | 44849 | 2022-11-15 | 2022-11-30 | 1 | 2022-11-30
24 | Goods | Udhampur | GU01000011 | ICT Infrastrucure | 4000 | RA 1 | Offline/Online | GFR 2017 and JKUT Financial rules | Yes | Yes | Direct/Bidding | National | 44851 | 44849 | 2022-11-15 | 2022-11-30 | 1 | 2022-11-30
25 | Goods | Udhampur | GU01000011 | Books ,softwares | 25000 | RA 1 | Offline/Online | GFR 2017 and JKUT Financial rules | Yes | Yes | Direct/Bidding | National | 44851 | 44849 | 2022-11-15 | 2022-11-30 | 1 | 2022-11-30
26 | Goods | Udhampur | GU01000011 | Facilitries for Trainees | 630000 | RA 1 | Offline/Online | GFR 2017 and JKUT Financial rules | Yes | Yes | Direct/Bidding | National | 44851 | 44849 | 2022-11-15 | 2022-11-30 | 1 | 2022-11-30
27 | Miscelleneous | Udhampur | GU01000011 | Notr covered above | 290000 | RA 1 | Offline/Online | GFR 2017 and JKUT Financial rules | Yes | Yes | Direct/Bidding | National | 44851 | 44849 | 2022-11-15 | 2022-11-30 | 1 | 2022-11-30
28 | Equipment, Furniture and other goods | Mendhar | GR01000028 | Chairs, Tables, sofa set | 3000000 | RA-1 | GEM | GFR-17/UT Jk applicable rules | YES | YES | ONLINE/GEM | NATIONAL | 44652 | 44709 | 2022-06-24 | 2022-06-09 |  | 2022-06-24 | Procurement done
29 | Minor civil work | Mendhar | GR01000028 |  | 250000 |  | Contract/ Tendering | GFR-17/UT Jk applicable rules | NO | NO | ONLINE/GEM | NATIONAL | 44653 | 44710 | 2022-06-25 | 2022-06-10 |  | 2022-06-25 | Procurement done
30 | ICT infrastructure | Mendhar | GR01000028 |  | 2500000 |  | GEM | GFR-17/UT Jk applicable rules | YES | YES | ONLINE/GEM | NATIONAL | 44654 | 44711 | 2022-06-26 | 2022-06-11 |  | 2022-06-26 | Procurement done
31 | Facilities for Trainees | Mendhar | GR01000028 |  | 150000 |  | GEM | GFR-17/UT Jk applicable rules | YES | YES | ONLINE/GEM | NATIONAL | 44655 | 44712 | 2022-06-27 | 2022-06-12 |  | 2022-06-27 | Procurement done
32 | Misc. | Mendhar | GR01000028 |  | 100000 |  | GEM | GFR-17/UT Jk applicable rules | YES | YES | ONLINE/GEM | NATIONAL | 44656 | 44713 | 2022-06-28 | 2022-06-13 |  | 2022-06-28 | Procurement done
33 | NIL | Kishtwar | GR01000006 | NA | NA | NA | NA | State procuremnt rule | Yes | Yes | GeM | National | NA | NA | NA | NA | NA | NA | NA
34 | Goods | BBIA | Capital expenditure- Machinery and equipment |  | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
35 | Goods | BBIA | Training of company supervisors | 736000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
36 | Goods | BBIA | Training of trainers in basic training provider | 280000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
37 | Goods | BBIA | Other (Training to AIC Staff & ITI faculty) | 1440000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
38 | Goods | BBIA | Tools and equipment | 1594000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
39 | Goods | BBIA | Training material | 1100000 | RA 2 |  | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
40 | Goods | BBIA | Insurance for apprentices | 300000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
41 | Goods | BBIA | Transport for apprentices | 350000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
42 | Goods | BBIA | Assessment and Certification cost | 200000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
43 |  | SPEND |  | NIL
44 | Goods | BBIa | Salary/fee and other cost for apprenticeship coordination | 1800000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
45 | Goods | BBIa | Office expenses and communication | 1200000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
46 | Goods | BBIA | Other (local tour, website hosying, audit fee) | 350000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12
47 | Goods | BBIA | Communication and outreach and workshop | 650000 | RA 2 | Mproc | UT J&K | No | No | Tender | Capital expenditure- Others……………………… | 2021-10-01 |  | 2022-09-30 |  | 12

## Notes
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International

## ITI Database
State/UT | District | NCVT MIS Code | ITI Name | Address
ANDAMAN AND NICOBAR ISLANDS | SOUTH ANDAMANS | GR35000001 | Government Industrial Training Institute | Dollygunj Port Blair
Andhra Pradesh | Kurnool | GR28000041 | Govt Industrial Training Institute | Opp. Poleramma Temple, Srisailam Project,
Andhra Pradesh | West Godavari | GR28000123 | Govt Industrial Training Institute | Undi Bhimavaram
Andhra Pradesh | Nellore | GR28000145 | Govt. Industrail Training Institute, Nellore | Nellore
Andhra Pradesh | Krishna | GR28000151 | Govt Industrial Training Institute | Vijayawada
Andhra Pradesh | Vizianagaram | GR28000154 | Govt Industrial Training Institute, Bobbili | Bobbili
Andhra Pradesh | Prakasam | GR28000155 | Govt Industrial Training Institute Boys, Ongole | NH - 5, Opp Mangamma Degree College, Ongole
Andhra Pradesh | Chittoor | GR28000182 | Govt Industrial Training Institute | PADMAVATHI PURAM, TIRUCHANUR ROAD, TIRUPATI
Andhra Pradesh | Guntur | GR28000206 | Govt Industrial Training Institute Tenali | Tenali Chinaravuru
Andhra Pradesh | East Godavari | GR28000238 | Govt Industrial Training Institute | Opp: Engg. College Pithapuram Road Kakinada
Andhra Pradesh | Nellore | GR28000270 | Govt. Industrial Training Institute for Girls,Nellore | Venkateshwarapuram,Nellore
Andhra Pradesh | Nellore | GR28000308 | Govt. Industrial Training Institute | Vill. & P.O Mandal - TADA
Andhra Pradesh | Chittoor | GR28000335 | Govt Industrial Training Institute | Puttur Road Konga Reddy Palli Chittoor
Andhra Pradesh | Cuddapah | GR28000386 | Govt. ITI, | Anjaneyapuram CHAKRAYAPETA post Kadapa District
Andhra Pradesh | Srikakulam | GR28000416 | Govt. ITI, Rajam | Rajam
Andhra Pradesh | Visakhapatnam | GU28000144 | Govt Industrial Training Institute (Old) Visakhapatnam | Visakhapatnam
Arunachal Pradesh | West Kameng | GR12000004 | Govt. Industrial Training Institute,Dirang | PO/PS-Dirang
Assam | Tinsukia | GR18000011 | Govt Industrial Training Institute, Tinsukia | I.T.I. Tinsukia, P.O.Borguri, Dist-Tinsukia, Assam Pin-786126
Assam | Jorhat | GU18000003 | Govt Industrial Training Institute Jorhat | I.T.I. Jorhat, P.O-Rajabari, Dist-Jorhat, Assam, Pin-785014
Assam | Nagaon | GU18000007 | Govt Industrial Training Institute-Nagaon | I.T.I Nagaon, P.O.& Dist. Nagaon, Assam, Pin-788001
Assam | Kamrup Metropolitan | GU18000022 | Govt Industrial Training Institute for Women, Guwahati | I.T.I. for Woman, Guwahati, P.O-Rehabari, Dist. Kamrup, Assam. Pin-781008
Assam | Nagaon | PR18000002 | Ajmal Rural Technolgoy & Demonstration Centre | A.R.T.D.C, Under K.V.K, Padumpukhuri, Kapashbari
BIHAR | MUNGER | GR10000033 | Govt Industrial Training Institute | Munger
Bihar | Gaya | GR10000032 | Govt Industrial Training Institute | Gaya
Bihar | Rohtas | GR10000034 | Govt Industrial Training Institute | Dehri-On-Sone
Bihar | Patna | GR10000041 | Govt Industrial Training Institute | Digaghat
Chandigarh | Chandigarh | GU04000002 | Govt Industrial Training Institute | Sector 28 C, Chandigarh
CHHATTISGARH | BALODA BAZAR BHATAPA | GR22000005 | Govt Industrial Training Institute, Kasdol, Distt-Baloda Bazar | VILL- ASNIND, POST- HATUAD BAZAR, TEH- KASDOL
CHHATTISGARH | BILASPUR | GR22000006 | Govt Industrial Training Institute for Women, Koni-Bilaspur, Distt-Bilaspur | 0
CHHATTISGARH | BALODA BAZAR BHATAPA | GR22000026 | Goverment Industrial Training Institute, Hathband, Distt-Baloda bazar | Hathband
CHHATTISGARH | KORBA | GR22000051 | Goverment Industrial Training Institute, Pali, Distt-Korba | Pali Pali
CHHATTISGARH | BEMETARA | GR22000061 | Govt. Industrial Training Institute, Parpodi, Distt-Bemetra | Parpodi
CHHATTISGARH | RAIPUR | GU22000021 | Goverment Industrial Training Institute, Raipur, Distt-Raipur | Saddu, Raipur
CHHATTISGARH | RAJNANDGAON | GU22000036 | Govt. Industrial Training Institute, Rajnandgaon, | Rajnandgoan (Pendri)
Chhattisgarh | Dhamtari | GR22000030 | Goverment Industrial Training Institute, Kurud,Distt-Dhamtari | Kurud,Distt-Dhamtari
Chhattisgarh | Bemetara | GR22000031 | Goverment Industrial Training Institute, Berla, Distt-Bemetra | Berla
Chhattisgarh | Durg | GU22000002 | Govt Industrial Training Institute for Women, Bhilai, Distt-Durg | P.O. Khursipar Bhilai
Chhattisgarh | Durg | GU22000003 | Govt Industrial Training Institute, Durg, Distt-Durg | Durg
Chhattisgarh | Raipur | GU22000065 | Govt. Industrial Training Institute, Mana, Distt-Raipur | Mana Camp, Mana, Raipur
Chhattisgarh | Durg | GU22000161 | Govt Industrial Training Institute, Bhilai, Distt-Durg | G. E. ROAD Khursipar, Bhilai
Chhattisgarh | Raipur | PR22000056 | Agashe Industrial Training Centre | Ashwani Nagar Mahadev Ghat Road
Chhattisgarh | Durg | PR22000095 | Puri ICT | Bhilai
Chhattisgarh | Baloda Bazar Bhatapa | PU22000150 | KAMLAKANT SHUKLA BHATAPARA | VILLAGE- DEORI, BHATAPARA
Chhattisgarh | Durg | PU22000188 | AAMDINAGAR PRIVATE ITI | HOSPITAL SECTOR NEAR HUDCO NEAR DAV SCHOOL HUD
Delhi | North East | GU07000025 | Government Sir C V Raman Industrial Training Institute Dheerpur | Dheerpur
Delhi | New Delhi | PU07000045 | Sri Guru Harkrishan Industrial Training Centre | 20 Block, Tilak Vihar, Tilak Nagar
GOA | NORTH GOA | GR30000012 | Bicholim Government Industrial Training Institute | Valshi, Bicholim, Goa
GOA | SOUTH GOA | GR30000017 | Farmagudi Government Industrial Training Institute | Farmagudi, Ponda - Goa
GUJARAT | PATAN | GR24000113 | INDUSTRIAL TRAINING INSTITUTE, BALISANA (Government) | Govt. ITI, BALISANA UNJHA -PATAN ROAD, NEAR GEB SUB STATION,, BALISANA, PATAN, PATAN, Gujarat
GUJARAT | PANCH MAHALS | GR24000225 | INDUSTRIAL TRAINING INSTITUTE, SHAHERA (Government) | Govt. ITI SHAHERA , KANKARI ROAD, AT PO TA SHAHERA
GUJARAT | SURAT | GR24000409 | INDUSTRIAL TRAINING INSTITUTE, ZANKHVAV (Government) | Govt. ITI, ZANKHVAV , NEAR CHC, ZANKHVAV, MANGROL, SURAT, Gujarat
GUJARAT | NAVSARI | GR24000425 | INDUSTRIAL TRAINING INSTITUTE, CHIKHLI (Government) | Govt. ITI, CHIKHLI OFFICE OF THE PRINCIPAL, KHUNDH,VANSADA ROAD NEAR ADARSH NIVASEE SCHOOL, CHIKHLI, Gujarat
GUJARAT | VALSAD | GR24000461 | INDUSTRIAL TRAINING INSTITUTE, KAPARADA (Government) | Govt. ITI, KAPARADA , BH. RENBASERA HOTEL,AT.PO.KAPARADA, TA.KAPRADA, DI.VALSAD, Gujarat
GUJARAT | PATAN | GU24000111 | INDUSTRIAL TRAINING INSTITUTE, HARIJ (Government) | Govt. ITI, HARIJ ,NEAR GOVT. NURSERY HARIJ -RADHAN
GUJARAT | BANAS KANTHA | GU24000120 | INDUSTRIAL TRAINING INSTITUTE, DEESA (Government) | Govt. ITI, DEESA , AT &amp;amp;amp;amp;amp; POST-
GUJARAT | KHEDA | GU24000207 | INDUSTRIAL TRAINING INSTITUTE, BALASINOR (Government) | Govt. ITI, BALASINOR , SEVALIA ROAD, BALASINOR, N
GUJARAT | VADODARA | GU24000235 | INDUSTRIAL TRAINING INSTITUTE (WOMEN), GORWA (WOMEN) (Government) | Govt. ITI, GORWA (WOMEN) , REFINERY ROAD, GORWA, VADODARA, Gujarat
GUJARAT | MAHESANA | GU24008049 | Government Industrial Training Institute Kadi | KADI-NANDASAN ROAD, OPP-BHAIRAV TEKARI, BESIDE ADA
Gujarat | Mahesana | GR24000127 | INDUSTRIAL TRAINING INSTITUTE, VIJAPUR (Government) | Govt. ITI, VIJAPUR BHAVSOR PATIYA , LADOL ROAD,
Gujarat | Mahesana | GR24000132 | INDUSTRIAL TRAINING INSTITUTE, VADNAGAR (Government) | Govt. ITI, VADNAGAR INDUSTRIAL TRAINING INSTITUTE
Gujarat | Kheda | GR24000209 | C.V.T.S.S.T. INDUSTRIAL TRAINING INSTITUTE, PALANA (Government) | Govt. ITI PALANA ,AT. PALANA, TA NADIAD , DIST KHEDA, Gujarat
Gujarat | Kheda | GR24000211 | SMT M.C.PATEL INDUSTRIAL TRAINING INSTITUTE, UTTARSANDA (Government) | Govt. ITI, UTTARSANDA , UTTARSANDA CROSSING,BHUMEL ROAD, UTTARSANDA, NADIAD, GUJARAT
Gujarat | Vadodara | GR24000222 | INDUSTRIAL TRAINING INSTITUTE, PADRA (Government) | Govt. ITI, PADRA ITI PADRA, STATION ROAD, PADRA, P. P. SHROFF HIGHSCHOOL CAMPUS, PADRA, PADRA, VADODARA, Gujarat
Gujarat | Vadodara | GR24000223 | INDUSTRIAL TRAINING INSTITUTE, VAGHODIYA (Government) | Govt. ITI, VAGHODIYA ITI WAGHODIA, KAMLAPURA ROAD, OPP DUTT PETROLPUMP, KAMLAPURA ROAD, WAGHODIA, VADODARA, Gujarat
Gujarat | Valsad | GR24000411 | INDUSTRIAL TRAINING INSTITUTE, DHARAMPUR (Government) | Govt. ITI, DHARAMPUR DASHERA PATI , NASIK ROAD, M
Gujarat | Surat | GR24000413 | INDUSTRIAL TRAINING INSTITUTE, BARDOLI (Government) | Govt. ITI BARDOLI,AT& PO TEN GAM,TA-BARDOLI ,DIST-SURAT, Gujarat
Gujarat | Surat | GR24000423 | INDUSTRIAL TRAINING INSTITUTE, OLPAD (Government) | Govt. ITI, OLPAD , ITI OLPAD,HATHISA ROAD,TA-OLPAD,DI-SURAT, SURAT, Gujarat
Gujarat | Sabar Kantha | GU24000103 | INDUSTRIAL TRAINING INSTITUTE, KHEDBRAHMA (Government) | SURTI KAMPAROAD NR BSNLOFFICE AT PO TA KHEDBRAHMA
Gujarat | Ahmadabad | GU24000109 | INDUSTRIAL TRAINING INSTITUTE, SARASPUR (Government) | OPP. GURUDHWARA,SARASPUR,AHMEDABAD -18, Gujarat
Gujarat | Sabar Kantha | GU24000114 | INDUSTRIAL TRAINING INSTITUTE, HIMATNAGAR (Government) | Govt. ITI, HIMATNAGAR , OPP-66 K.V. G.E.B. SUBSTA
Gujarat | Patan | GU24000121 | INDUSTRIAL TRAINING INSTITUTE, PATAN (Government) | Govt. ITI, PATAN , At & Post - Rajpur , Ta & Dist - Patan, PATAN, Gujarat
Gujarat | Sabar Kantha | GU24000130 | INDUSTRIAL TRAINING INSTITUTE (W), IDAR (WOMEN) (Government) | Govt. ITI, IDAR (WOMEN) , KUKDIYA ROAD, LALODA,
Gujarat | Jamnagar | GU24000303 | INDUSTRIAL TRAINING INSTITUTE, JAMNAGAR (Government) | Govt. ITI, JAMNAGAR , SUMAIR CLUB ROAD, OPP. ST DE
Gujarat | Kutch | GU24000307 | INDUSTRIAL TRAINING INSTITUTE, GANDHIDHAM (Government) | Govt. ITI, GANDHIDHAM G.I.D.C AREA, NR. OSLO CINE
Gujarat | Rajkot | GU24000323 | INDUSTRIAL TRAINING INSTITUTE, DHORAJI (Government) | Govt. ITI, DHORAJI INDUSTRIAL TRAINING INSTITUTE, JUNAGADH ROAD, NEAR LOHANA VADI, Gujarat
Gujarat | Kutch | GU24000329 | INDUSTRIAL TRAINING INSTITUTE, BHUJ (Government) | Govt. ITI, BHUJ MUNDRA ROAD, BH.LEWA PATEL HOSPITAL, -1, Gujarat
Gujarat | Surat | GU24000406 | INDUSTRIAL TRAINING INSTITUTE, MANDVI (SURAT) (Government) | Govt. ITI, MANDVI (SURAT) ITI MANDVI, B&amp;#39;H
Gujarat | Tapi | GU24000420 | INDUSTRIAL TRAINING INSTITUTE, VALOD (Government) | Govt. ITI, VALOD , BARDOLI ROAD,AT&amp;PO:VALOD,
Gujarat | Valsad | GU24000429 | INDUSTRIAL TRAINING INSTITUTE (WOMEN), VALSAD (WOM | ovt.VALSADW,lilapor,auranga rd,nr small bridgerd
Gujarat | Surat | GU24000460 | WOMEN INDUSTRIAL TRAINING INSTITUTE, SACHIN (WOMEN) (Government) | Govt. ITI, SACHIN (WOMEN), NEAR PHC HEALTH CENTER, B/H PARDI-KANDE KHADI, SURAT-NAVSARI ROAD, SACHIN, TA. CHORYASI, DI.SURAT
Gujarat | Mahesana | GU24008040 | MEHSANA Government I T I | 204, GIDC PHASE-1, NR-WATER TANK, MODHERA CROSS R
Gujarat | Jamnagar | GU24008048 | INDUSTRIALTRAINING INSTITUTE JAMNAGAR CITY(MAHILA) | NEAR SEVEN ROAD CIRCLE,INDIRA MARG,I.T.I CAMPUS,JA
Gujarat | Mahesana | PR24000508 | SHETH SHRI R.V.RAVAL PRIVATE ITI, GIA GOZARIA | AT.PO-GOZARIA,TA.DI- MAHESANA, Gujarat
Gujarat | Sabar Kantha | PR24000542 | RAJKRUPA EDUCATION TRUSHT PRIVATE ITI, GIA BHILODA (Grant In Aid) | GIA ITI, BHILODA , AT&PO:RAJENDRANAGAR,TA:BHILODA,DIST:SABARKANTHA, RAJENDRANAGAR, BHILODA, SABARKANTHA, Gujarat
Gujarat | Anand | PR24000616 | C.K.PATEL TECHNICAL INSTITUTE PRIVATE ITI, GIA NAR (Grant In Aid) | GIA ITI, NAR , OPP YOGI RICE MILL, NR. RAILWAY S
Gujarat | Surat | PR24000805 | SMT.B.H.SHAH(KARJANWAL A) I.T.I.(P) | COLLEGE CAMPUS, NH 8,PO- KAMREJ CHAR RASTA
Gujarat | Patan | PR24005130 | SHRI K.V.PATEL INDUSTRIAL TRAINING CHANSMA PRIVAT | PATAN ROAD, COLLAGE CAMPUS RUPPUR-CHANASMA, DIST P
Gujarat | Anand | PU24000656 | SHRI RAMKRISHNA SEVA MANDAL SANCHALIT ANAND PRIVA | SF ANAND ITC , VIVEKANAND MEDAN , NR -GREED, LAMB
HARYANA | KAITHAL | GU06000013 | Govt. Industrial Training Institute, Kaithal | Kaithal
HARYANA | SONIPAT | GU06000055 | Govt. Industrial Training Institute Gannaur | Ganaur
HARYANA | JIND | GU06000062 | Govt. Industrial Training Institute , Jind | Jind
HARYANA | FARIDABAD | GU06000071 | Govt. Industrial Training Institute (Women) Faridabad | Faridabad
HARYANA | HISAR | GU06000072 | Govt. Industrial Training Institute Barwala | Barwala
Haryana | Sirsa | GR06000033 | Govt. Industrial Training Institute Nathusari Chopta | Nathusari Chopta
Haryana | Ambala | GR06000059 | Govt. Industrial Training Institute, Barara | Barara
Haryana | Rewari | GR06000064 | Govt. Industrial Training Institute Kund Manethi | Kund Manethi
Haryana | Yamunanagar | GR06000088 | Govt. Industrial Training Institute Sadhora | Sadhora
Haryana | Jhajjar | GR06000092 | Govt. Industrial Training Institute Bhaproda | Bhaproda
Haryana | Hisar | GU06000004 | Govt. Industrial Training Institute (Women) Hisar | Hisar
Haryana | Sonipat | GU06000006 | Govt. Industrial Training Institute Sonepat | Sonipat
Haryana | Rohtak | GU06000018 | Govt. Industrial Training Institute Hassangarh | Hassangarh
Haryana | Kaithal | GU06000028 | Govt. Industrial Training Institute (Women) Kaithal | Kaithal
Haryana | Fatehabad | GU06000036 | Govt. Industrial Training Institute Tohana | Tohana
Haryana | Rewari | GU06000045 | Govt. Industrial Training Institute Rewari | Rewari
Haryana | Sonipat | GU06000046 | Govt. Industrial Training Institute Gohana | Gohana
Haryana | Kurukshetra | GU06000058 | Govt. Industrial Training Institute, Kurukshetra | Kurukshetra
Haryana | Rohtak | GU06000073 | Govt. Industrial Training Institute Meham | Meham
Haryana | Panchkula | GU06000081 | Govt. Industrial Training Institute Kalka | Vill. Ghatiwala PO Pinjore Pin 134102
Haryana | Karnal | GU06000091 | Govt. Industrial Training Institute Nissing | Nissing
Himachal Pradesh | Mandi | GR02000025 | Govt Industrial Training Institute, Mandi | Govt. ITI Mandi Tehsil sadar Distt Mandi H.P Pin 1
Himachal Pradesh | Bilaspur | GR02000028 | Govt Industrial Training Institute, Bilaspur | Nihal Sector, Near Industrial Area Bilaspur, Tehsil Sadar, District Bilaspur 174001
Himachal Pradesh | Sirmaur | GR02000029 | Govt Industrial Training Institute Paonta Sahib | Paonta Sahib
Himachal Pradesh | Solan | GR02000033 | Govt Industrial Training Institute for Women Nalagarh | Nalagarh
Himachal Pradesh | Solan | GR02000034 | Govt Model Industrial Training Institute Nalagarh Dist Solan HP | Nalagarh Dist Solan, HP
Himachal Pradesh | Kangra | GR02000035 | Govt ITI Palampur | Govt. ITI Palampur
Himachal Pradesh | Una | GR02000076 | Govt. ITI Bangana | Tehsil Bangana, Distt Una
Himachal Pradesh | Solan | GR02000085 | Govt Industrial Training Institute, Solan | Solan
Himachal Pradesh | Kullu | GR02000087 | Govt Industrial Training Institute Shamshi | Shamshi
Himachal Pradesh | Mandi | GR02000094 | Govt. ITI Jogindernagar | P.O Jogindernagar, Tehsil Jogindernagar, Distt Man
Himachal Pradesh | Kullu | GR02000101 | Govt. Industrial Training Insutute Sainj | Sainj
Himachal Pradesh | Shimla | GR02000107 | Govt Industrial Training Institute Jubbal | Jubbal
Himachal Pradesh | Hamirpur | GR02000108 | Govt. Industrail Training Insutute Naduan at Rail | Naduan at Rail, Post office Rail Tehsil Nadaun
Himachal Pradesh | Kangra | GR02000131 | Govt Industrial Training Institute Shahpur | V.P.O. Shahpur, Tehsil Shahpur, Dist. Kangra, H.P.
Himachal Pradesh | Mandi | GR02000133 | Govt Industrial Training Institute for Persons with Disabilities Sunder Nagar | BBMB Colony Sundernagar
Himachal Pradesh | Kangra | GR02000136 | Shaheed Surinder Singh, Govt. Industrial Training Institute Jawali | Jawali, Kangra
Himachal Pradesh | Sirmaur | GR02000207 | Govt. ITI Rajgarh | Rajgarh
Himachal Pradesh | Kullu | GU02000031 | Govt Industrial Training Institute, Kullu | Post office Dhalpur, Tehsil &amp;amp;amp;amp;amp;
Himachal Pradesh | Kangra | GU02000124 | Govt ITI Baijnath | Baijnath
JAMMU AND KASHMIR | ANANTNAG | GR01000003 | Govt Industrial Training Institute Anantnag | Ashajipora Anantnag
JAMMU AND KASHMIR | BARAMULLA | GR01000004 | Govt Industrial Training Institute Baramulla | Kralhar Baramulla, near Govt Boys Degree College
JAMMU AND KASHMIR | KISHTWAR | GR01000007 | Govt Industrial Training Institute Kishtwar | Kishtwar
JAMMU AND KASHMIR | POONCH | GR01000028 | Govt Industrial Training Institute Mendhar | Gohlad, Mendhar
JAMMU AND KASHMIR | GANDERBAL | GR01000030 | Govt Industrial Training Institute Ganderbal | Duderhama, Gandebal
JAMMU AND KASHMIR | UDHAMPUR | GU01000011 | Govt Industrial Training Institute Udhampur | Near District Hospital
JHARKHAND | DHANBAD | GR20000007 | Govt Industrial Training Institute | Behind Polytechnic sadar
JHARKHAND | BOKARO | GR20000008 | Govt. Industrial Training Institute, Bokaro | Chas-
JHARKHAND | EAST SINGHBUM | GR20000039 | Govt. Industrial Training Institute Jamshedpur | Burmamines jamshedpur
KARNATAKA | CHITRADURGA | GR29000231 | Government Industrial Training Institute (W) | Stadium Road Chitradurga 577501
KARNATAKA | HASSAN | GU29000050 | Govt Industrial Training Institute B.M Road, Hassan | B.M Road
Karnataka | Chamarajanagar | GR29000206 | Govt. ITI(W), Gundlupet | Govt. ITI(W),Ooty Road Gundlupet,-571111
Karnataka | Koppal | GR29000211 | Govt ITI Kukanoor | Taluk: Yelaburga
Karnataka | Tumkur | GR29000226 | Govt Industrial Training Institute for Women Tiptur | Padmashri Nagar Hassan Road
Karnataka | Mandya | GR29000400 | Government Industrial Training Institute, Maddur | Somanahalli, Maddur, Mandya Dist.
Karnataka | Mysore | GR29000470 | Govt. Industrial Training Institute, H.D.Kote | H.D. Kote
Karnataka | Bagalkot | GR29000472 | Govt Industrail Training Institute Bilagi | Bilagi Road
Karnataka | Chamarajanagar | GR29000925 | Govt. ITI, Beguru | Gundlupet Tq
Karnataka | Dakshina Kannada | GU29000044 | Government Industrial Training Institute (Men),Mangalore | Kadri Hills, Mangalore -575004
Karnataka | Belgaum | GU29000045 | Govt Industrial Training Institute (Men) Udyambagh, Belgaum | Udyambagh, Blegaum
Karnataka | Mysore | GU29000053 | Government Industrial Training Institute , N R Mohalla Mysore-07 | N R Mohalla, Mysore-570007
Karnataka | Chikmagalur | GU29000065 | Govt Industrial Training Institute, Chikmagalur | Thilak Park Road Vijayapura Chikkamagaluru-577101
Karnataka | Mandya | GU29000066 | Govt Industrial Training Institute, Mandya | Industrial Estate, First stage, Sugar Town Post
Karnataka | Belgaum | GU29000154 | Government Industrial Training Institute for (Women) Belgaum | UDYAMBAG BELGAUM
Karnataka | Mandya | GU29000158 | Govt Industrial Training Institute, Malavalli | Government Industrial Training Institute, Behind KSRTC Bus Stand, Opposite Munciff Court, Malavalli Town
Karnataka | Bangalore | GU29000214 | Govt Industrail Training Centre for Women Hosur Road | Hosur Road
Karnataka | Bagalkot | GU29000242 | Govt Industrial Training Institute(W) Bagalkot | Navanagar
Karnataka | Dakshina Kannada | GU29000255 | Govt Industrial Training Institute for Women,Mangalore | Konchady Post, Air port Road, Mangalore - 575008
Karnataka | Mandya | GU29000317 | Government Industrial Training Institute ,Pandavap | Behind Hemavathi Quarters, K.Bettahalli Road, Pand
Karnataka | Udupi | GU29000428 | Govt Industrial Training Institute Manipal, Udupi | Pragathinagara, Manipal, Udupi Taluk
Karnataka | Dakshina Kannada | PR29000170 | Sri Dharmasthala Manjunatheshwara ITI | Venur, Belthangady Taluk
Kerala | Palakkad | GR32000029 | Government Industrial Training Institute Kuzhalmannam | Perumkunnam P O, Kuzhalmannam
Kerala | Kasaragod | GR32000107 | Government Industrial Training Institute Kasaragod | Vidyanagar P O
Kerala | Thrissur | GR32000223 | Government Industrial Training Institute Chalakkudy | Chalakkudy P O
Kerala | Kottayam | GR32000231 | Government Industrial Training Institute | Ettumanoor P O
Kerala | Palakkad | GR32000236 | Government Industrial Training Institute Malampuzha | Malampuzha P O
Kerala | Kozhikode | GR32000238 | Government Industrial Training Institute Kozhikode | Malikkadavu, Karuvissery.P O
Kerala | Alappuzha | GR32000241 | Government Industrial Training Institute Chengannur | Angadikal South P.O Chengannur Alappuzha
Kerala | Thiruvananthapuram | GR32000246 | Government Industrial Training Institute Attingal | Attingal P O
Kerala | Malappuram | GR32000247 | Government Industrial Training Institute Areacode | Ugrapuram P.O.
Kerala | Wayanad | GR32000307 | Krishna Mohan Memorial Government Industrial Training Institute | Maniyancode P O, Kalpetta
Kerala | Thrissur | GR32000311 | K.Karunakaran Smaraka Government Industrial Training Institute | Valiyaparambu, Kuruvilassery. P.O, Mala
Kerala | Kollam | GR32000426 | Government Industrial Training Institute Chathannoor | Chathannnor
Kerala | Kozhikode | GR32000613 | Government Industrial Training Institute for Women Kozhikode | Malikkadavu, Karuvissery P. O
Kerala | Thiruvananthapuram | GU32000222 | Government Industrial Training Institute Chackai | Chackai P.O.
Kerala | Ernakulam | GU32000242 | Government Industrial Training Institute Kalamassery | H.M.T Colony P O
Kerala | Kollam | GU32000310 | Government Industrial Training Institute for Women Kollam | Manayilkulangara, Thirumullavaram P O
Kerala | Ernakulam | GU32000353 | Government Industrial Training Institute for Women Kalamassery | H.M.T Colony P O
Kerala | Ernakulam | PR32000252 | Balanagar Technical Institute Private Industrial Training Institute | Mookkannur P.O.
Kerala | Thrissur | PR32000254 | R GANESH MEMORIAL VICTORY PRIVATE INDUSTRIAL TRAINING INSTITUTE | OLLUKKARA P O
MADHYA PRADESH | DEWAS | GR23000009 | Govt Industrial Training Institute,Dewas | VIKAS NAGAR CHOURAHA A.B. ROAD DEWAS
MADHYA PRADESH | SHAJAPUR | GR23000036 | Govt Industrial Training Institute,Shajapur | A.B Road shajapur
MADHYA PRADESH | SEONI | GR23000127 | Govt Industrial Training Institute Chhapara | SANJAY COLONY CHHAPARA
MADHYA PRADESH | SHIVPURI | GR23000242 | Govt Industrial Training Institute,Shivpuri | Guna Bypass Jhansi Road Shivpuri.
MADHYA PRADESH | SEONI | GR23000253 | Govt Industrial Training Institute, Seoni | CHUNA BHATTI CHIDIYA PARARI SEONI
MADHYA PRADESH | KATNI | GR23000255 | Govt Industrial Training InstituteKatni | NEAR ROSHAN NAGAR, NKJ Katni
MADHYA PRADESH | TIKAMGARH | GR23000259 | Govt Industrial Training Institute Tikamgarh | Tikamgarh
MADHYA PRADESH | HARDA | GR23000284 | Govt Industrial Training Institute, Harda | KHANDWA ROAD HARDA
MADHYA PRADESH | CHHATARPUR | GU23000006 | Govt Industrial Training Institute,Chhatarpur | Sharswati Nagar ,Naya Panna Naka Panna road ,Chhat
MADHYA PRADESH | ANUPPUR | GU23000017 | Govt Industrial Training Institute, Anuppur | Near Tulsi College Jaithari Road Anuppur
MADHYA PRADESH | JHABUA | GU23000053 | Govt Industrial Training Institute, Rajwada, Jabua | anas nadi ke paas] indore road, jhabua
MADHYA PRADESH | KHANDWA | GU23000248 | Govt Industrial Training Institute,khandwa | ITI sinhara road, khandwa
Madhya Pradesh | Balaghat | GR23000003 | Govt Industrial Training Institute,Balaghat | WARD NO.1, BUDHI ROAD BALAGHAT
Madhya Pradesh | Betul | GR23000019 | Govt Industrial Training Institute for Women,Betul | Industrial Area, Kosami , Betul (M.P.)
Madhya Pradesh | Ratlam | GR23000030 | Govt Industrial Training Institute,Ratlam | Ratlam
Madhya Pradesh | Raisen | GR23000139 | Govt Industrial Training Institute Mandideep | Near Jiletine SQ.,Old AKVN Block,Mandideep
Madhya Pradesh | Chhindwara | GR23000251 | Govt Industrial Training InstituteChhindwara | Chakkar Road CHHINDWARA
Madhya Pradesh | Khargon | GU23000054 | Govt Industrial Training Institute, Khargon | umarkhaali road, lal mati, rehu road khargone
Madhya Pradesh | Umaria | GU23000058 | Govt Industrial Training Institute, Umaria | GRAM DABRAUHA KACHARWAR ROAD UMARIA
Madhya Pradesh | Sidhi | GU23000060 | Govt Industrial Training Institute, Singrauli | Village Telai Post Kachani mamla
MAHARASHTRA | NAGPUR | GR27000011 | Government Industrial Training Institute, Nagpur, | Shraddhanand Peth Opp Blind School
MAHARASHTRA | BULDHANA | GR27000026 | Government Industrial Training Institute, Khamgaon, Dist: Buldhana | Jalamb Road, Khamgaon.
MAHARASHTRA | AHMEDNAGAR | GR27000048 | Government Industrial Training Institute, Shevgaon, Dist: Ahmednagar | Pathardi Road, At Post Shevgaon
MAHARASHTRA | NANDURBAR | GR27000053 | Government Industrial Training Institute (Adivasi), Nandurbar, Dist: Nandurbar | Near Shani Mandir, G.T.P. College Road, Nandurbar
MAHARASHTRA | JALGAON | GR27000086 | Government Industrial Training Institute, Bhusawal, Dist: Jalgaon | Jamner Road, Near Saibaba Mandir
MAHARASHTRA | NASHIK | GR27000114 | Government Industrial Training Institute (Adivasi), Kalwan, Dist: Nashik | At Kolhopur Phata, Post - Manur
MAHARASHTRA | NANDURBAR | GR27000120 | Government Industrial Training Institute (Adivasi), Navapur, Dist: Nandurbar | Dhanrat Road
MAHARASHTRA | AMRAVATI | GR27000152 | Government Industrial Training Institute, Nandgaon Khandeshwar, Dist: Amravati | Chandurrly Road
MAHARASHTRA | YAVATMAL | GR27000156 | Government Industrial Training Institute (Adivasi), Pandharkawada, Dist: Yavatmal | Sonbardi Road
MAHARASHTRA | CHANDRAPUR | GR27000172 | Government Industrial Training Institute (Adivasi) | Asifabad Rao Near Shivaji Collage
MAHARASHTRA | SANGLI | GR27000242 | Government Industrial Training Institute, Tasgaon, Dist: Sangli | Datta Mala, Vasumbe Phata, Manerajuri Road
MAHARASHTRA | NAGPUR | GR27000265 | Government Industrial Training Institute, Kalmeshwar, Dist: Nagpur | At. Kalmeshwar
MAHARASHTRA | NASHIK | GR27000272 | Government Industrial Training Institute, Sinnar, Dist: Nashik | At Post Sinnar
MAHARASHTRA | NASHIK | GR27000286 | Government Industrial Training Institute (Adivasi), Igatpuri, Dist: Nashik | At Post Igatpuri
MAHARASHTRA | YAVATMAL | GR27000290 | Government Industrial Training Institute, Ghatanji, Dist: Yavatmal | Belora Road
MAHARASHTRA | WASHIM | GR27000306 | Government Industrial Training Institute, Karanja Lad, Dist: Washim | Darwha Road
MAHARASHTRA | THANE | GR27000354 | Government Industrial Training Institute, Bhiwandi, Dist: Thane | Bhadvad, Near Police Line
MAHARASHTRA | KOLHAPUR | GR27000372 | Government Industrial Training Institute, Radhanagari, Dist: Kolhapur | Near St Depo Opp-gajanan Maharaj Mandir
MAHARASHTRA | JALNA | GR27000411 | Government Industrial Training Institute, Ghansavangi, Dist: Jalna | Rajegaon Road
MAHARASHTRA | YAVATMAL | GR27000415 | Government Industrial Training Institute (Adivasi), Ralegaon, Dist: Yavatmal | Kalamb Road
MAHARASHTRA | YAVATMAL | GR27000416 | Government Industrial Training Institute (Adivasi) | At. Maregaon
MAHARASHTRA | YAVATMAL | GR27000417 | Government Industrial Training Institute (Adivasi), Kalamb, Dist: Yavatmal | At. Kalamb
MAHARASHTRA | AHMEDNAGAR | GR27000422 | Government Industrial Training Institute, Sangamner, Dist: Ahmednagar | At- Gunjalwadi, Post-Rajapur
MAHARASHTRA | AKOLA | GR27000438 | Government Industrial Training Institute, Murtijapur, Dist: Akola | Karanja Road
MAHARASHTRA | YAVATMAL | GR27000465 | Government Industrial Training Institute, Ner, Dist: Yavatmal | Manikwada Road
MAHARASHTRA | WASHIM | GR27000518 | Government Industrial Training Institute, Manora, Dist: Washim | M.I.D.C. Area Devthana Road
MAHARASHTRA | MUMBAI | GU27000008 | Government Industrial Training Institute, Mumbai-11, Dist: Mumbai Sahar | 374, Sane Guruji Marg, Near Agripada Police Statio
MAHARASHTRA | AURANGABAD | GU27000016 | Government Industrial Training Institute, Aurangabad, Dist: Aurangabad | MIDC Area Railways Station Road
MAHARASHTRA | GONDIA | GU27000028 | Government Industrial Training Institute, Gondia, Dist: Gondia | Govt. ITI, Fulchur peth, Goregaon Road, Gondia
MAHARASHTRA | NASHIK | GU27000155 | Government Industrial Training Institute (Woman), Nashik, Dist: Nashik | Old Mumbai Agra Road
MAHARASHTRA | AKOLA | GU27000225 | Government Industrial Training Institute (Woman), Akola, Dist: Akola | Akot Stand
MAHARASHTRA | PUNE | GU27000226 | Government Industrial Training Institute (Woman), Pune, Dist: Pune | Parihar Chowk, Aundh
MAHARASHTRA | RATNAGIRI | GU27000240 | Government Industrial Training Institute (Woman), Ratnagiri, Dist: Ratnagiri | Nachane Road
Maharashtra | Nanded | GR27000010 | Government Industrial Training Institute, Nanded, Dist: Nanded | VIP Road,Near Mahatma Phule Statue
Maharashtra | Akola | GR27000012 | Government Industrial Training Institute, Akola, Dist: Akola | Ratanlal Plot , Akola
Maharashtra | Amravati | GR27000013 | Government Industrial Training Institute, Amravati, Dist: Amravati | Morshi Road,Amravati
Maharashtra | Satara | GR27000019 | Government Industrial Training Institute, Karad, Dist: Satara | Vidhya Nagar, Saidapur
Maharashtra | Solapur | GR27000022 | Government Industrial Training Institute, Solapur, Dist: Solapur | Vijapur Road
Maharashtra | Ahmadnagar | GR27000023 | Government Industrial Training Institute, Ahmednagar, Dist: Ahmednagar | At Post Ahmednagar
Maharashtra | Nashik | GR27000024 | Government Industrial Training Institute, Nashik, Dist: Nashik | Babubhai Rathi Chowk, Trambak Road, Satpur
Maharashtra | Wardha | GR27000027 | Government Industrial Training Institute, Pulgaon, Dist: Wardha | Nachangaon Road
Maharashtra | Latur | GR27000030 | Government Industrial Training Institute, Latur, Dist: Latur | Shivaji Chowk
Maharashtra | Parbhani | GR27000036 | Government Industrial Training Institute, Parbhani, Dist: Parbhani | Jintur Road
Maharashtra | Jalna | GR27000062 | Government Industrial Training Institute, Jalna, Dist: Jalna | Near ST Workshop, Aurangabad Road, Chandanzeera, J
Maharashtra | Nashik | GR27000063 | Government Industrial Training Institute (Adivasi), Dindori, Dist: Nashik | Umrale Road, At Post . Dindori
Maharashtra | Buldana | GR27000080 | Government Industrial Training Institute, Buldana, Dist: Buldhana | Malkapur Road
Maharashtra | Gadchiroli | GR27000084 | Government Industrial Training Institute (Adivasi), Gadchiroli, Dist: Gadchiroli | Gadchiroli
Maharashtra | Kolhapur | GR27000135 | Government Industrial Training Institute, Gadhinglaj, Dist: Kolhapur | Sadhana Mal, Shendri Road
Maharashtra | Latur | GR27000143 | Government Industrial Training Institute, Nilanga, Dist: Latur | Bidar Road
Maharashtra | Nagpur | GR27000445 | Government Industrial Training Institute, Butibori, Dist: Nagpur | Butibori, P-9, MIDC Area
Maharashtra | Nashik | GR27000701 | Government Industrial Training Institute (Adivasi), Deola, Dist: Nashik | At Post -DEOLA TAL-DEOLA
Maharashtra | Pune | GU27000009 | Government Industrial Training Institute, Pune, Dist: Pune | Parihar Chowk, Aundh, Pune, Maharashtra
Maharashtra | Dhule | GU27000014 | Government Industrial Training Institute, Dhule, Dist: Dhule | Old Agra Road, Deopur
Maharashtra | Jalgaon | GU27000015 | Government Industrial Training Institute, Jalgaon, Dist: Jalgaon | National High Way No 6, Jalgaon
Maharashtra | Satara | GU27000018 | Government Industrial Training Institute, Satara, Dist: Satara | Molacha Odha Karanje Tarf
Maharashtra | Kolhapur | GU27000021 | Government Industrial Training Institute, Kolhapur, Dist: Kolhapur | Kalamba Road
Maharashtra | Sangli | GU27000029 | Government Industrial Training Institute, Sangli, Dist: Sangli | Industrial Estate
Maharashtra | Bid | GU27000031 | Government Industrial Training Institute, Beed, Dist: Beed | Nagar Road
Maharashtra | Thane | GU27000040 | Government Industrial Training Institute, Thane, Dist: Thane | Road No. 28, Ramnagar, Wagale Industrial Estate
Maharashtra | Thane | GU27000041 | Government Industrial Training Institute, Ambernat | Old Bhendipada, Kalyan Badlapur Road (West)
Maharashtra | Mumbai | GU27000050 | Government Industrial Training Institute, Mulund, Dist: Mumbai Sahar | Balasaheb Thakurwadi, Mithagar Road
Maharashtra | Pune | GU27000066 | Government Industrial Training Institute, Pimpri Chinchwad, Dist: Pune | Telco Road, Behind Bajaj Auto, Ajanta Nagar, Secto
Maharashtra | Wardha | GU27000078 | Government Industrial Training Institute, Wardha, Dist: Wardha | Arvi Naka Mahda Colony
Maharashtra | Nagpur | GU27000151 | Government Industrial Training Institute (Woman), Nagpur, Dist: Nagpur | Pt. Malviya Road, Sitabuildi
Maharashtra | Thane | GU27000230 | Government Industrial Training Institute (Woman), Thane, Dist: Thane | C/o Govt. Tech. High School, Kopari Colony (East)
Maharashtra | Yavatmal | GU27000037 | Government Industrial Training Institute, Yavatmal, Dist: Yavatmal | Dhamangaon Road
Maharashtra | Washim | GU27000307 | Government Industrial Training Institute, Washim, Dist: Washim | Civil Line washim
Maharashtra | Jalgaon | PR27000187 | Late, G. S. Varade Private Industrial Training Institute | Old Bus Stand Road, Near J. E. School, Muktainagar
Maharashtra | Nandurbar | PR27000247 | Jamia Private Industrial Training Institute | Near Amlibari Fata
Maharashtra | Ahmadnagar | PR27000497 | Shirdi Sai RuralInstitute'S Industrial Training Institute | At.Po-Rahata Tal:Rahata Dist:Ahmednagar.
Maharashtra | Jalgaon | PR27000521 | Hindi Seva Mandalache, Shri Sant Gadge Baba Private Industrial Training Institute, Bhusawal. | D.L.Hindi High School Campus, Shivaji Nagar, Bhusawal. Dist.Jalgaon
MANIPUR | IMPHAL WEST | GR14000001 | Govt Industrial Training Institute Imphal (Takyel) | Takyel
Meghalaya | East Khasi Hills | GR17000007 | Govt Industrial Training Institute, Shillong | RYNJAH, SHILLONG
MIZORAM | AIZAWL | GU15000001 | Govt Industrial Training Institute, Aizawl | ITI Veng, Aizawl, Mizoram
Odisha | Koraput | GR21000502 | Gopa Bandhu Govt.ITI | Ambaguda, Via- Jaipur
Odisha | Ganjam | GR21000519 | Govt. Industrial Training Institute, Hinjlicut | At-Pochilima,Po-Makarjhola,via-Kanchuru,Ps-Hinjilicut
Odisha | Kendujhar | GU21000498 | Govt Industrial Training Institute, Barbil | At -Barbil Po:- Matkambeda
Odisha | Sundargarh | GU21000499 | Govt Industrial Training Institute, Rourkela | At-Panposh Industrial Estrate, Rourkela
Odisha | Cuttack | GU21000500 | Madhusudan Industrial Training Institute, Cuttack | At-BOSE Campus, PO- SCB Medical College
Odisha | Khordha | GU21000510 | Govt Industrial Training Institute, Bhubaneswar | Nayapali Bhubaneswar
Odisha | Kandhamal | GU21000511 | Govt Industrial Training Institute, Phulbani | At / PO- Phulbani
Odisha | Balasore | GU21000524 | Govt. Industrial Training Institute, Balasore | O.T Road,Angaragadia,Balasore
Odisha | Ganjam | GU21000525 | Govt Industrial Training Institute, Berhampur | Po:-Engineering School Berhampur
Odisha | Kalahandi | GU21000526 | Govt Industrial Training Institute, Bhawanipatna | giti bhawanipatna
PUNJAB | PATIALA | GR03000005 | Govt Industrial Training Institute Nabha, Patiala | Chhintawala Road Near Over Bridge Nabha
PUNJAB | MANSA | GR03000078 | Govt Industrial Training Institute(SC) | Govt. I.T.I. Mansa (SC)
PUNJAB | LUDHIANA | GU03000029 | Govt Industrial Training Institute | Gill Road
PUNJAB | BARNALA | GU03000096 | Govt Industrial Training Institute | DHANAULA ROAD BARNALA
Punjab | Rupnagar | GR03000011 | Govt Industrial School for Girls | Morinda
Punjab | Kapurthala | GR03000017 | Govt Industrial Training Institute | SATNAMPURA
Punjab | Patiala | GR03000022 | Govt Industrial Training Institute | Near SOS,Rajpura -140401 (Distt. Patiala)
Punjab | Fatehgarh Sahib | GR03000027 | Govt. Industrial Training Institute, Bassi Pathana | Bassi Pathana
Punjab | Rupnagar | GR03000037 | Industrial Training Institute, Nangal | Govt. ITI Nangal, Nangal Township, Nangal, Distt. Ropar, Punjab - 140124
Punjab | Pathankot | GR03000039 | Goverment Industrial Training Institute | Pathankot
Punjab | Sahibzada Ajit Singh Nagar | GR03000087 | Govt Industrial Training Institute | Handesra Road, Lalru
Punjab | Pathankot | GR03000119 | Govt. ITI, Kathua Road, Bamial | Kathua road, Bamial
Punjab | Patiala | GU03000013 | Govt Industrial Training Institute | Near PRTC Workshop Model Town
Punjab | Faridkot | GU03000031 | Goverment Industrial Training Institute | Faridkot
Punjab | Gurdaspur | GU03000032 | Goverment Industrial Training Institute | Batala Road Qadian
Punjab | Gurdaspur | GU03000036 | Goverment Industrial Training Institute | Batala
Punjab | Bathinda | GU03000041 | Goverment Industrial Training Institute | Mansa Road Bathinda
Punjab | Rupnagar | GU03000045 | Govt Industrial Training Institute | Nagal Road Ropar
Punjab | Hoshiarpur | GU03000050 | Goverment Industrial Training Institute | Sector-3 Talwara T/ Ship
Punjab | Mansa | GU03000051 | Goverment Industrial Training Institute | Bhhiki Road budhlada
Punjab | Gurdaspur | GU03000067 | P K Goverment Industrial Training Institute | Gurdaspur-pathankot G.T. Road
Punjab | Faridkot | GU03000076 | Goverment Industrial Training Institute (SC) | Faridkot
Punjab | Sahibzada Ajit Singh Nagar | GU03000094 | Govt Industrial Training Institute for Women | Phase 5, Near Water Tank, Mohali
Punjab | Fazilka | PR03000185 | Maharaja Agarsen Industrial Training Centre Alamgarh | Ganga Nagar Road Alamgarh Abohar
RAJASTHAN | JAIPUR | GR08000079 | Government Industrial Training Institute Jaipur | BANI PARK,
RAJASTHAN | JAIPUR | GR08000083 | Government Women Industrial Training Institute | Banipark
RAJASTHAN | AJMER | GR08000088 | Government Industrial Training Institute, Beawar | By Pass Road Ganeshpura beawar
RAJASTHAN | AJMER | GR08000096 | Government Women Industrial Training Institute | Makrupura
RAJASTHAN | AJMER | GR08000417 | Government Industrail Training Instiute Parasia Kishangarh | Parasia Kishangarh
RAJASTHAN | PALI | GR08000962 | Government Industrial Training Institute | FCI ROAD,INDUSTRIAL AREA, PALI (RAJASTHAN)
RAJASTHAN | JODHPUR | GR08000984 | Government Women Industrial Training Institute | Near Saras Doodh Dairy, Opp. Rajasthan Udyog, Heav
RAJASTHAN | KOTA | GR08001001 | Government Industrial Training Institute Sangod | Anta Road Sangod
RAJASTHAN | PALI | GR08001005 | Government Industrial Training Institute Jaitaran | Vill-Patus Mertacity Road Jaitaran
RAJASTHAN | JODHPUR | GU08000939 | Government Industrial Training Institute, JODHPUR | NEAR SHASTRI CIRCLE, JODHPUR
RAJASTHAN | KOTA | GU08000940 | Government Industrial Training Institute, KOTA | D.C.M ROAD, KOTA
RAJASTHAN | UDAIPUR | GU08000941 | Government Industrial Training Institute, UDAIPUR | UDAIPUR
RAJASTHAN | GANGANAGAR | GU08000947 | Government Industrial Training Institute, SRI GANGANAGAR | ABOHAR ROAD, SRI GANGANAGAR
RAJASTHAN | JHALAWAR | GU08000954 | Government Industrial Training Institute, JHALAWAR | KALI SINDH ROAD, JHALAWAR
Tamil Nadu | Virudhunagar | GR33000034 | Government Industrial Training Institute,Virudhunagar | Soolakarai
Tamil Nadu | Tiruchirappalli | GR33000046 | Government Industrial Training Institute, Trichy | Thanjai Main Raod, Thiruverambur,
Tamil Nadu | Thiruvallur | GR33000051 | Government Industrial Training Institute, Ambattur | Ambattur
Tamil Nadu | Dindigul | GR33000061 | Government Industrial Training Institute,Dindigul | Natham Road, Kullanampatty, Dindigul.,
Tamil Nadu | Kancheepuram | GR33000066 | Goverment Industrial Training Institute, Chengalpattu | Vempakkam Post,chengalpattu
Tamil Nadu | Thoothukkudi | GR33000074 | Government Industrial Training Institute,,Thoothukudi | Korampallam
Tamil Nadu | Namakkal | GR33000540 | Government Industrial Training Institute(W),Namakkal | Tamilnadu Motel, Paramathi Via, Kirambur Post
Tamil Nadu | Perambalur | GR33000565 | Government Industrial Training Institute,Perambalur | Indhra Nagar, Thaneerpanthal, Perambalur.
Tamil Nadu | Cuddalore | GU33000037 | Government Industrial Training Institute,Cuddalore | Semmandalam, Cuddalore
Tamil Nadu | Salem | GU33000040 | Government Industrial Training Institute,Salem | Yercaud Main Road, Hasthampatti PO.
Tamil Nadu | Coimbatore | GU33000058 | Government Industrial Training Institute,Coimbatore | Mettupalayam Road, GN Mills - Post
Tamil Nadu | Madurai | GU33000060 | Government Industrial Training Institute,Madurai | K.pudur, Madurai.,
Tamil Nadu | Sivaganga | GU33000568 | Government Industrial Training Institute,Sivagangai | Muthupatti, Sivagangai
Tamil Nadu | Tiruchirappalli | PR33000268 | Don Bosco Private Industrial Training Institute, Trichy | Manakkal Lalgudi
Tamil Nadu | Virudhunagar | PR33000301 | Ramco Private Industrial Training Institute, Virudhunagar | Kumarasamy Raja Nagar Post, Rajapalayam.
Tamil Nadu | Ariyalur | PR33000597 | P A C Ramasamy Raja Private Industrial Training Institute | Govindapuram
Telangana | Adilabad | GR36000019 | Govt Industrial Training Institute | Mancherial
Telangana | Rangareddy | GR36000038 | Govt District Level Training Centre / ITI | Market road Subhash Nagar, Vikara Bad Ranga Reddy Dist
Telangana | Mahbubnagar | GR36000069 | Govt Industrial Training Institute for Girls | Kalwakurthy
Telangana | Khammam | GR36000136 | Govt. Industrial Taining Institute for Girls | H.No.6-182, Jublipura Beside Jubli Club Telukapally
Telangana | Karimnagar | GR36000137 | Govt Industrial Training Institute for Girls | Karimnagar - Post
Telangana | Nalgonda | GR36000208 | Govt. ITI | H.No. 13-304, KYR Colony, Subhash Nagar, Aler
Telangana | Medak | GU36000011 | Govt Industrial Training Institute | Main Raod opp CSI church Sangareddy Medak
Telangana | Hyderabad | GU36000013 | Govt Industrial Training Institute, Musheerabad | R-TC-X- Road, Hyderabad 500020, TS
Telangana | Nizamabad | GU36000070 | Govt Industrial Training Institute for Girls | Shivajinagar,Varni Road,Nizamabad
Telangana | Rangareddy | GU36000122 | Govt. Industrial Training Institute | H.No: 1-13/A, beside Water Reservior, Main Road Lothkunta Alwal, Ranga Reddy Dist
Tripura | North Tripura | GR16000008 | Govt Industrial Training Institute (Mission Tilla) Dharma Nagar | Mission Tilla Dharma Nagar, Mission Tilla, P/o- East Kameswar, Dharmanagar.
Tripura | South Tripura | GR16000010 | Govt. Industrial Training Institute, Belonia | Belonia
Tripura | West Tripura | GU16000004 | Govt Industrial Training Institute for Women | P.O. Indranagar, Agartala
UTTAR PRADESH | GORAKHPUR | GR09000754 | Government ITI, Chargawan, Distt- Gorakhpur | Government ITI, Chargawan, Distt- Gorakhpur
UTTAR PRADESH | KANPUR NAGAR | GR09000832 | Government ITI, (Mahila), Lal Bangla, Kanpur, Kanpur Nagar | Government ITI, (Mahila), Lal Bangla, Kanpur, Kanp
UTTAR PRADESH | CHANDAULI | GR09001591 | Government Industrial Traning Institute, Chandauli | Vill. Rewsa Po. Janso ki Mandai, District Chandaul
UTTAR PRADESH | LUCKNOW | GU09000559 | Government ITI, World Bank Mahila, Lucknow | GITI WORLD BANK (W) ALIGANJ
UTTAR PRADESH | LALITPUR | GU09001562 | Government ITI, Lalitpur | SIDDHAN ROAD SIDDHANPURA LALITPUR
UTTAR PRADESH | FATEHPUR | GU09001565 | Government ITI, Fatehpur | Govt. I.T.I. Fatehpur I.T.I. Road Fatehpur
UTTAR PRADESH | MIRZAPUR | GU09001592 | Government ITI, Chhanbey, Mirzapur | Government ITI, Chhanbey, Mirzapur
UTTAR PRADESH | SITAPUR | GR09000120 | Government ITI, Sitapur | KHAIRABAD, SITAPUR
UTTAR PRADESH | BARABANKI | GR09000134 | Government ITI, Barabanki | Village Mahuamau Post Darahra, Jahangirabad, Barab
Uttar Pradesh | Allahabad | GR09000548 | Government ITI, Naini, Allahabad | mirzapur road , naini , allahabad
Uttar Pradesh | Rae Bareli | GR09000747 | Government ITI, Raebareli | Government ITI, Raebareli
Uttar Pradesh | Bareilly | GR09000750 | Government ITI, Collectorganj, Bareilly | NH 24 Rampur Road C B Ganj Bareilly
Uttar Pradesh | Sant Kabir Nagar | GR09001282 | Government ITI, Mehdawal, Sant Kabir Nagar | GITI MEHDAWAL SANTKABIR NAGAR
Uttar Pradesh | Bijnor | GR09001468 | Government ITI, Bijnor | Government ITI, Bijnor
Uttar Pradesh | Varanasi | GR09001474 | Government ITI, Karaundi, Varanasi | Karaundi, (Near B.H.U.) District. Varanasi
Uttar Pradesh | Lucknow | GR09001476 | Government ITI, Aliganj, Lucknow | Aliganj Lucknow
Uttar Pradesh | Meerut | GR09001483 | Government ITI, Bachcha Park, Meerut | GITI BACHCHA PARK MEERUT
Uttar Pradesh | Meerut | GR09001497 | Government ITI, World Bank Mahila, Meerut | saket meerut
Uttar Pradesh | Rae Bareli | GR09001503 | Government ITI, Mahila, Raebareli | Directorate of Training & Placement, Bansmandi Cha
Uttar Pradesh | Meerut | GR09001541 | Government ITI, Saket, Meerut | Government ITI, Saket, Meerut
Uttar Pradesh | Gautam Buddha Nagar | GR09001590 | Government ITI, Jewar, Gautam Buddh Nagar | GITI JEWER JHUPPA PANWAL ROAD G.B.NAGAR
Uttar Pradesh | Shahjahanpur | GU09001558 | Government ITI, Shahjahanpur | Roza
Uttar Pradesh | Jhansi | GU09001561 | Government ITI, Jhansi | GOVT. ITI GWALIOR ROAD JHANSI
Uttar Pradesh | Lakshmipur Kheri | GU09001571 | Government ITI, Lakhimpur Kheri | Government ITI, Lakhimpur Kheri
Uttar Pradesh | Gonda | GU09001575 | Government ITI, Gonda | ROJGAR BHAWAN GURU GOVIND SINGH MARG LUCKNOW
Uttar Pradesh | Kanpur Nagar | PR09001207 | A.P.V. ITC - Kanpur Nagar | 117/H-1/209 Pandu Nagar Kanpur Nagar
Uttar Pradesh | Pilibhit | PR09001740 | Balaji Private ITI , Tanakpur Road Saidpur, Pilibhit | Tanakpur Road Saidpur, Pilibhit
Uttar Pradesh | Kanpur Nagar | PU09001814 | J.K. Center Technician Training Private ITI , Doda Nagar, Kanpur | 81-B Industrial Area, Dada Nagar, Kanpur-208022
Uttar Pradesh | Jhansi | PU09001984 | Maa Pitambra Pvt Iti | Shivpuri Road, JMK Motors, Behind JK Hospital, Nan
UTTARAKHAND | PAURI GARHWAL | GR05000075 | Govt. Industrial Training Institute Saldmahadev | Government Industrial Training Institute Saldma
UTTARAKHAND | UDAM SINGH NAGAR | GU05000069 | Govt. Industrial Training Institute Dineshpur | Government Industrial Training Institute Dineshp
UTTARAKHAND | TEHRI GARHWAL | GU05000098 | Govt. Industrial Training Institute Chamba | Government Industrial Training Institute Chamba
UTTARAKHAND | DEHRADUN | GU05000102 | Govt. Industrial Training Institute Kalsi | Government Industrial Training Institute Kalsi
Uttarakhand | Nainital | GR05000109 | Govt. Industrial Training Institute Betalghat | Government Industrial Training Institute Betalgh
Uttarakhand | Nainital | GR05000114 | Govt. Industrial Training Institute Tandi | Government Industrial Training Institute Tandi
Uttarakhand | Hardwar | GU05000082 | Govt. Industrial Training Institute Haridwar | Government Industrial Training Institute Haridwar
Uttarakhand | Nainital | GU05000120 | Govt. Industrial Training Institute Ramnagar | Government Industrial Training Institute Ramnagar
West Bengal | Puruliya | GR19000013 | Govt Industrial Training Institute, Purulia | P.O.- Raghunathpur, Dist - Purulia, Pin - 723133
West Bengal | Kolkata | GR19000015 | Govt Industrial Training Institute, Tollyganj | Tollyganj
West Bengal | Uttar Dinajpur | GR19000016 | Govt. Industrial Training Institute Raiganj | Karnajora, Uttar Dinajpur, PIN 733130
West Bengal | Paschim Medinipur | GR19000022 | GOVT Industrial Training Institute Jhargram | Jhargram
West Bengal | Darjiling | GR19000025 | Govt Industrial Training Institute Siliguri | Siliguri
West Bengal | Murshidabad | GR19000030 | Govt. Industrial Training Institute Berhampore | Banjetia, Berhampore, P.O.- Cossimbazar Raj
West Bengal | Maldah | GR19000032 | Govt Industrial Training Institute, Malda | MAHESHMATI, P.O. + DIST. MALDA. PIN 732101. WEST B
West Bengal | Kolkata | GR19000035 | Govt Industrial Training Institute Gariahat | 10 AND 10 BYE 1, GARIAHAT ROAD
West Bengal | Nadia | GR19000050 | BPC Industrial Training Center(sponsored) | P.O.Krishana
West Bengal | Paschim Medinipur | GR19000053 | Govt Industrial Training Institute Midnapore | P.O.-RANGAMATI, DIST-PASCHIM MIDNAPORE. PIN - 721
West Bengal | Birbhum | GR19000054 | Govt Industrial Training Institute Suri | DIST- BIRBHUM,PIN - 731 101. PH: 03462 255-453
West Bengal | Hugli | GR19000057 | Govt Industrial Training Institute, Hooghly (Sahaganj) | P.O. - SAHAGANJ, DIST-HOOGHLY. PIN - 712 104. PH: 033 2631-2327
West Bengal | Koch Bihar | GR19000158 | Mathabhanga Government ITI | Vill :- Uttar Barai Bari, PO :- Mather Khuti, PS:-
West Bengal | Puruliya | GR19000159 | Manbazar Government ITI | PO + PS :- Manbazar, Dist :- Purulia
West Bengal | Dakshin Dinajpur | GR19000160 | Hili Government ITI College | Hili, Mulahat, Pin-733126
West Bengal | Nadia | GR19000166 | Nakashipara Government ITI | Vill + PO + PS :- Nakashipara, Dist :- Nadia, West
West Bengal | Bankura | GR19000178 | Khatra Government ITI | Vill + PO + PS :- Khatra, Dist :- Bankura, West Be
West Bengal | Dakshin Dinajpur | GR19000194 | Tapan Government ITI College | Mouza: Tapan, Plot No: 805, 815, 844, 845, JL No: 63, Block: Tapan
West Bengal | South Twenty Four Parganas | GR19000198 | Sagar Government ITI | PLOT NO.-174,JL NO.-42,MOUZA-PURUSATAMPUR,P.O-BAGB
West Bengal | Barddhaman | GR19000211 | BHATAR Government ITI | Plot No.-2992(P),JL No.-31,Mouza-Kashipur,P.O-Bhat
West Bengal | Paschim Medinipur | GR19000212 | Binpur-II Government ITI | P.O+Mouza-Sahari,P.S-Belpahari,Block- Binpur-II,Di
West Bengal | South Twenty Four Parganas | GR19000214 | Canning I Government ITI College | PO: Tangrakhali, PS: Canning, South 24 PGS
West Bengal | Koch Bihar | GR19000217 | DINHATA GOVERNMENT ITI | EXCHANGE PARA, OPPOSITE OF MAHAMAYA CINEMA HALL, D
West Bengal | Paschim Medinipur | GU19000147 | Salboni Government ITI | Salboni
West Bengal | North Twenty Four Parganas | GU19000168 | Halisahar Government ITI College | Halisahar, North 24 Parganas, West Bengal
West Bengal | Paschim Medinipur | GU19000197 | Garbeta Government ITI | Garbeta
West Bengal | Puruliya | PR19000144 | Manbhum Pvt ITI | Vill: MAUTORH, P.O. MAUTORH, P.S.ï¿½RAGHUNATHPUR
West Bengal | Paschim Medinipur | PU19000064 | Salboni ITI | Paschim Medinipur
Maharashtra | AHMEDNAGAR | GR27000499 | Government Industrial Training Institute, Rahuri, Dist: Ahmednagar | Navyug Colony, Tandulwadi, Station Road
Maharashtra | AHMEDNAGAR | GR27000421 | Government Industrial Training Institute, Shrigonda, Dist: Ahmednagar | Wadali Road
Maharashtra | WARDHA | GR27000353 | Government Industrial Training Institute, Hinganghat, Dist: Wardha | At Rimdoh Jam Road
Maharashtra | THANE | GR27000051 | Government Industrial Training Institute (Adivasi), Wangaon, Dist: Thane | Vangaon Chinchani Road
Maharashtra | AHMEDNAGAR | GR27000092 | Government Industrial Training Institute, Jamkhed, Dist: Ahmednagar | Karmala Road
Puducherry | PONDICHERRY | GR34000012 | Government Industrial Training Institut, Nettapakkam, Puducherry | Madam Street
Puducherry | PONDICHERRY | GU34000011 | Government Industrial Training Institute for Women, Puducherry | Nethaji Subbash Chandra Bose Street, Vambakeerapal
JAMMU AND KASHMIR | SAMBA | GR01000035 | Govt Industrial Training Institute Samba | Samba
Sikkim | EAST DISTRICT | GR11000001 | Government Industrial Training Institute,Rangpo,East Sikkim | Mining, Rangpo-737132, East Sikkim
Nagaland | MOKOKCHUNG | GR13000002 | Govt. Industrial Training Institute, Mokokchung | P.B.139, Mokokchung , Nagaland
Delhi | EAST | GU07000008 | H J BHABHA INDUSTRIAL TRAINING INSTITUTE | H J BHABHA INDUSTRIAL TRAINING INSTITUTE KHICHRIPU
Delhi | NEW DELHI | GR07000049 | Lala Hans Raj Gupta ITI Bhorgarh, Narela | DSIDC Industrial Complex Bhorgarh Narela